## Progress Payments
POWELL RESIDENCE ¦ PROGRESS PAYMENT TRACKER
Contractor: Saddlewood Contracting LLC ¦ Owners: Mark & Heather Powell ¦ 3526 Emerson St, San Diego CA 92106 |  |  |  | Invoice #: 3526-09 |  | Date: 09/09/2026
PAYMENT SUMMARY (Cash Received to Date)
Check #253 — 04/30/2026 |  |  |  |  | 50000
Check #258 — 05/21/2026 |  |  |  |  | 60000
Owner Draw (ref. ________) — 05/31/2026 |  |  |  |  | 90000
Owner Payment (ref. ________) — 06/16/2026 |  |  |  |  | 73109.58
Owner Payment (ref. ________) — 07/01/2026 |  |  |  |  | 65000
Owner Payment (ref. ________) — Inv #3526-05 — 07/16/2026 |  |  |  |  | 29800
Owner Deposit (ref. ________) — Inv #3526-06 — 07/28/2026 |  |  |  |  | 57426.72
Owner Payment (ref. ________) — Inv #3526-07 — 08/14/2026 |  |  |  |  | 30000
Owner Payment (ref. ________) — Inv #3526-08 — __/__/2026 |  |  |  |  | 35500
TOTAL PAID TO DATE
DESCRIPTION OF WORK | CONTRACT $ (Original Quoted) | CHANGE ORDERS (+ Increase / − Decrease) | TOTAL $ (Current Contract) | % COMPLETE | PREVIOUSLY PERFORMED (Prior to This Invoice) | CURRENT $ DUE (This Invoice) | TOTAL TO DATE (Performed + Draw)
Crawl Space ($10,000 of $15,015 completed) | 15015 | 0 |  |  |  | 0
Attic [TBD — Pricing Pending] | 0 | 0 |  | 0% |  | 0
Roof & Skylights [TBD — Pricing Pending] | 0 | 0 |  | 0% |  | 0
✔ Roof Repairs [100% COMPLETE] | 0 | 6000 |  | 100% |  | 0
✔ Interior Walls & Framing [100% COMPLETE] | 0 | 14368.5 |  | 100% |  | 0
Ceiling Heights & Framing | 0 | 0 |  | 0% |  | 0
✔ HVAC — A/C Registers (CO) [100% COMPLETE] [A/C registers labor & materials — balance of HVAC scope still TBD] | 0 | 2500 |  | 100% |  | 0
✔ Stucco [100% COMPLETE] | 27300 | 10000 |  | 100% |  | 0
Kitchen ($39,000 of $89,512 completed) | 89512 | 0 |  |  |  | 0
Primary Bath ($22,000 of $62,055 completed) | 62055 | 0 |  |  |  | 0
Guest Bath ($16,500 of $31,500 completed) | 31500 | 0 |  |  |  | 0
Powder Room | 13492 | 0 |  | 0% |  | 0
Laundry Room ($10,000 of $23,572 completed) | 23572 | 0 |  |  |  | 0
Closets & Mark's Office ($15,000 of $41,737 completed) | 41737 | 0 |  |  |  | 0
Fireplaces | 28087 | 0 |  | 0% |  | 0
Doors ($23,841.08 of $26,252 completed) | 14752 | 11500 |  |  |  | 0
✔ Flooring [100% COMPLETE] [labor $45,675 + material CO $21,251.72 — billed in full, paid] | 45675 | 21251.72 |  | 100% |  | 0
Electrical (Whole House) ($79,000 of $90,000 completed) | 105000 | -15000 |  |  |  | 0
Plumbing (Whole House) ($46,800 of $70,000 completed) | 94500 | -24500 |  |  |  | 0
✔ Insulation [100% COMPLETE] | 0 | 13600 |  | 100% |  | 0
Drywall ($46,000 of $47,250 completed) | 49350 | -2100 |  |  |  | 0
Painting & Baseboards ($42,000 of $49,087 completed) | 49087 | 0 |  |  |  | 0
Rear Deck [TBD — Pricing Pending] | 0 | 0 |  | 0% |  | 0
Final Clean | 3675 | 0 |  | 0% |  | 0
Contingency | 35280 | 0 |  | 0% |  | 0
Overhead 15% [TBD — Pricing Pending] | 0 | 0 |  | 0% |  | 0
PROJECT TOTALS |  |  |  | —
FINANCIAL SUMMARY
Total Contract Value (All Current Pricing incl. Change Orders)
Total Work Performed to Date (Value Earned)
Total Cash Paid to Date (9 payments received — see Payment Summary above)
Balance Due on Completed Work (Performed − Paid)
New Advance Draws Requested — Next-Phase Mobilization
TOTAL DUE THIS INVOICE (#3526-09) = Total to Date − Paid
Overall Project % Complete (Performed ÷ Contract)
Total Remaining — Future Work Not Yet Started
KEY: [ Green ] = 100% Complete [ Yellow ] = In Progress [ Gray ] = TBD / Pricing Pending [ Orange CO ] = Price Increase [ Blue CO ] = Price Decrease / Savings [ Red Current Due ] = Billed This Invoice
NOTES: (1) Owner payment of $35,500.00 received __/__/2026 paid Invoice #3526-08 in full (Kitchen $19,000 progress, Guest Bath $6,500 progress, Laundry Room $5,000 progress, Painting & Baseboards $5,000 progress — all now recognized as completed work, no longer billed this invoice). Total cash paid to date: $490,836.30. (2) CURRENT DUE THIS INVOICE (#3526-09) = $0.00 — no new billing this period. (3) CRAWL SPACE: $10,000 of $15,015 complete (66.60%) — no new billing this invoice. (4) KITCHEN: $39,000 of $89,512 complete (43.57%) — fully paid via Invoice #3526-08; no new billing this invoice. (5) PRIMARY BATH: $22,000 of $62,055 complete (35.45%) — no new billing this invoice. (6) GUEST BATH: $16,500 of $31,500 complete (52.38%) — fully paid via Invoice #3526-08; no new billing this invoice. (7) LAUNDRY ROOM: $10,000 of $23,572 complete (42.42%) — fully paid via Invoice #3526-08; no new billing this invoice. (8) CLOSETS & MARK'S OFFICE: $15,000 of $41,737 complete (35.94%) — no new billing this invoice. (9) DOORS: $23,841.08 of $26,252 complete (90.82%) — no new billing this invoice. (10) ELECTRICAL (WHOLE HOUSE): $79,000 of $90,000 complete (87.78%) — no new billing this invoice. (11) PLUMBING (WHOLE HOUSE): $46,800 of $70,000 complete (66.86%) — no new billing this invoice. (12) DRYWALL: $46,000 of $47,250 complete (97.35%) — no new billing this invoice. (13) PAINTING & BASEBOARDS: $42,000 of $49,087 complete (85.56%) — fully paid via Invoice #3526-08; no new billing this invoice. (14) 100% COMPLETE: Roof Repairs $6,000 (change order); Interior Walls & Framing $14,368.50 (change order); HVAC — A/C Registers (CO) $2,500 (change order); Stucco $37,300 (incl. +$10,000 change order); Flooring $66,926.72 (incl. +$21,251.72 change order); Insulation $13,600 (change order). (15) Change orders to date: Roof Repairs +$6,000, Interior Walls & Framing +$14,368.50, HVAC — A/C Registers (CO) +$2,500, Stucco +$10,000, Doors +$11,500, Flooring +$21,251.72, Electrical (Whole House) −$15,000, Plumbing (Whole House) −$24,500, Insulation +$13,600, Drywall −$2,100 (net +$37,620.22). (16) Items marked TBD are pending owner decisions, change-order pricing, or site evaluation. Pending change orders issued for owner approval (double-layer perimeter walls, rear deck, block walls, landscape) are NOT reflected in this tracker and will be added only upon written owner approval.